## Processing Timeline and Steps
Who | Step 1: Concurrent Filing (EAD / AP / AOS / I-526E) | Day | Step 1: Concurrent Filing (AOS / I-526E) Foreign national enters the U.S. with a Conditional Green Card (valid for 1 to 1.5 years).
Yugandhar | Introduce client to EB-5 attorney to begin the process. | 1
Investor | Provide sources of funds (SOF) list and complete intake questionnaire. | 1
Attorney | Replies OK with SOF | 2
Attorney gives approval | Attorney reviews - if SOF is good, case is cleared to move forward. | 1
If investor agrees, proceed | Attorney sends engagement form; sign and pay $10,000 advance to start work. | 2
Investor | Sign and pay | 2
Attorney | Receive detailed SOF documentation list (bank statements, medical, immigration records, etc.) with instructions. | 3
Investor | Complete USCIS-approved medical exam (within 2 weeks). | 3
Investor | Prepare and upload all documents to attorney’s Dropbox. | 13
Investor | Send passport photos to attorney’s office. | 13
Attorney and investor | Attorney reviews; resolves any issues (back-and-forth communication). | 18
Attorney | Once SOF is approved, attorney gives clearance to fund investment. | 20
Medical office | Send sealed SOF package to attorney’s office. | 20
Investor | Transfer investment funds to project escrow account. | 21
Yugandhar | Receive proof of funds received. | 21
Investor | Pay remaining attorney fees after invoice is issued. | 21
Attorney | Attorney prepares final documents for signature. | 23
Attorney | Attorney submits concurrent filing to USCIS (EAD / AP / AOS / I-526E). | 25
Receipt notice | I526E | 40
Escrow attorney | After I-526E submission, release funds to project. | 45 | Conditional 1 to 1.5 year
USCIS | USCIS schedules biometrics appointment. | 60 to 120 days
USCIS | Receive EAD/AP cards for all applicants and dependents. | 60 to 120 days
USCIS | USCIS reviews SOF and approves I-526E. | 6 months to 12 months
USCIS | If visa is current, conditional Green Card is issued. | 6 to 12 months |  | From the date of receiving the Green Card, after 5 years, you can apply for U.S. citizenship and then receive a U.S. passport.
Wait | Project creates jobs as required. | 2 years
Project | Submit supporting documentation. | 1 yr 9 months | 6 to 12 months
Attorney | Apply for removal of conditions (showing investment maintained and jobs created). | 6 to 12 months
USCIS | Receive permanent Green Card.